## RAID LOG
| RAID Log | [6 empty] | Total | Critical | High | Moderate | Low | Negligible
R1 | Risk | Low prediction accuracy due to synthetic dataset | High | Medium | Improve dataset quality and add relevant features | Pranav Sukale | Open
R2 | Risk | Overfitting of ML model | High | Medium | Use cross-validation and regularization | Pranav Sukale | Open
R3 | Risk | Streamlit UI navigation bugs | Medium | Medium | Continuous UI testing after updates | Pranav Sukale | In Progress
A1 | Assumption | Students provide accurate input data | Medium | - | Add input validation constraints | Pranav Sukale | Valid
A2 | Assumption | Synthetic dataset reflects real trends | High | - | Plan to integrate real dataset later | Pranav Sukale | Valid
I1 | Issue | Top-3 recommendation initially showing single output | Medium | - | Updated logic to return top 3 predictions | Pranav Sukale | Resolved
I2 | Issue | Reset button not clearing selections | Medium | - | Implemented session state reset | Pranav Sukale | Resolved
D1 | Dependency | Clean dataset required before model training | High | - | Complete preprocessing phase first | Pranav Sukale | Active
D2 | Dependency | Trained model required before UI integration | High | - | Finalize model before deployment | Pranav Sukale | Active
R4 | Risk | Low model accuracy (~50%) | High | High | Apply feature engineering and hyperparameter tuning | Pranav Sukale | Open
R5 | Risk | Dataset size too small (200 rows) | High | High | Increase dataset size and reduce noise | Pranav Sukale | Open
R6 | Risk | Class imbalance in placement prediction | Medium | Medium | Use resampling techniques (SMOTE/class weights) | Pranav Sukale | In Progress
A3 | Assumption | CGPA correlates with placement outcome | Medium | - | Validate using correlation analysis | Pranav Sukale | Valid
A4 | Assumption | Internships influence placement | Medium | - | Evaluate feature importance | Pranav Sukale | Valid
I3 | Issue | Confusion matrix shows imbalance in predictions | High | - | Testing class weights adjustment | Pranav Sukale | In Progress
D3 | Dependency | Feature scaling required for Logistic Regression | Medium | - | Apply standardization before training | Pranav Sukale | Active